## Sheet1
RFC 2821bis issues list
Note: ??? Implies "issue may still be open even though text has changed" or, with the stuff assigned to Ned "waiting"… cref is also marked ???
-03 Issue# | -02 Issue# | -01 Issue# | Description | Status | Comments
closed | closed | 0a | Remove "ignorant" from 7.1 | Done - 02b | Promoting harmony
closed | closed | 0b | MAIL FROM validation and EHLO validity tests | No action | "Editorial judgment"
closed | 1 | 1 | Format of domain - trailing period | 02c. Sufficient? ??? | So far inconclusive, but leaning toward "no dot, but some explanation about TLDs' - 20070328. Bunch of ccTLDs have MX records. Note sent to ICANN 20070329 to try to find out what for. Draft text in -02c 20070413.
2 | 2 | 2 | Check VRFY/EXPN text in Section 3.5.3 | Ned??? | See Ned's note, 20070329. Ned to send text, I hope. Placeholder added -02c, 20070413.
closed? | 3 | 3 | EHLO validation in sect 4.1.4, para 6 |  | Tony Finch suggests MUST-> SHOULD, Hector has new language (some of which, IMO, goes too far). Notes on 20070329). Pulled text from 4.1.4 to eliminate redundancy; added more xrefs.
closed | closed | 4 | Sect 4.2.1 (Reply Codes 4yz 5yz) "encouraged" -> SHOULD | Done 03b (see issue 16) | Hector suggests (20070309) a rewrite to MAY based on no enforcement. David Skoll suggests MUST NOT. Closed 4yz to SHOULD in -02, 5yz to SHOULD NOT in -03 (part of issue 16)
5 | 5 | 5 | Sect 4.4. Syntax of ID in trace | Fixed -02c | Leave alone or change "string" to "atom". Changed to Atom per consensus note. Might need to be Dot-string, per Ellermann 20070403
closed | closed | 6 | Precedence error -- ABNF technical problem w/ grouping | Fixed -02b | Editorial: need parens to group alternatives
7 | 7 | 7 | Switch conformity language to 2119 form |  | Added to list 20070328
closed | 8 | 8 | Number of recipients/ number of transactions per connection | Dead? | 2821is clear on recipients needs separate extension to do either definitively. Guidance on transactions/ connection?? Probably dead - no text needed 20070416
closed | closed | 9 | Table of requirements and/or index and/or more items as sections. | Fixes in -02b. Done | 4.5.3.1 and 4.5.3.2 lists converted to sections in -02b. TOC directives patched to include these. More would fall into the "rework" category.
10 | 10 | 10 | Add discussion of mail rerouting via 251/551 to Security Considerations | Ned??? | Ned's note, 20070329. Ned to send text, I hope. Placeholder inserted in 02c.
closed | closed | 11 | Change instances of "A RR" to language that is IPv6-inclusive) | Fixed - 02b | Discussed on list, number not formally assigned. Seems like a no-brainer.
closed | closed | 12 | IPv6 issues with MX records | New text inserted, 02c | Discuss implications of MX records with IPv6-only targets. Handed off to ADs Draft text tentatively approved.
closed | closed | 13 | Syntax for parameters that contain email addresses. | Done 02c | Use xtext from RFC 3461 section 4: http://www.apps.ietf.org/rfc/rfc3461.html#page-6
closed | closed | 14 | Continuation lines for 220 Greeting? | Inserted 02c | Tony Finch 20070405. Says 20070406 that multiline greetings are common and cause no interop problems.
closed | closed | 15 | Syntax change for reply lines to allow for continuation? | Fixed 02c | Tony Finch 20070405. Seems like clear bug. Note cref comment about Reply-text production.
closed? | 16 | 16 | General use of "is permitted", etc | Done 03b | Klensin note, 20070407. General feeling is "should edit". … Get 02 posted first, then do this.
closed | closed | 17 | Should text be clarified to single code in continuations | Done 02c | Hector et al 20070409-11. After list discussions, text changed to require one code 20070413.
closed | closed | 18 | Should text be clarified to prohibit 1yz codes without extensions | Done 02c | Hector et al 20070409-11. After list discussions, text changed to clearly prohibit 20070413. Put in: Any unrecognized code SHOULD be treated as an error (4yz or 5yz under discussion 20070423)
19 | 19 | 19 | Comments on literals in EHLO - remove either "Explained-literal" or the text in 4.1.1.1 that describes it. |  | Tony Finch/ Mark Mallett 20070412
20 | 20 | 20 | RFC3552 and Security Considerations |  | Do we need to do anything?
21 | 21 | --- | Bounce / reject improvements in section 6.2 | Collapse into issue 25 - section 6.2 isn't all that is affected | Wasn't that debate ruled out of order?
22 | 22 | --- | May->Should, Should-> Must changes for return-paths in 4.4 |  | Conversation with Keith 20070426 - note to list. Change text to remove apparent contradiction.
23 | 23 | --- | Section 2.3.11 now defines "reply". Should there be a specific, numbered, definition for "command"? If so, text welcome. |  | Mark E Mallett 20070418
24 | 24 | --- | Revise all ABNF to make a closed system starting with a definition for "command" or "command-verb" |  | Pro: It would be nicer. Con: odds of being able to do this in a reasonable amount of time and without introducing new errors are low to none. Frank and Arnt to rework after all substantive issues are concluded.
25 | 25 | --- | Change all text that implies non-delivery messages to prohibit them entirely or permit them only with source authentication. |  | Frank Ellerman, repeatedly. This one needs to be definitively closed, again, IMO (JcK). Make sure any changes are reflected in 2821bis-03 6.2 and see Hector's "2821bis-03 comments" note of 20070426
closed? | 26 | --- | Revise description of reverse-paths to prevent repeated citations of "server adds its own…" | ???Text in 03c | I think this is a dead issue (JcK)
closed? | 27 | --- | Straighten out and define terminology for talking about headers | Done 03c | Pete Resnick note 20070423. Header section/ Header field/ Received clause
closed? | 28 | --- | Client behavior with unrecognized code | Text in 03c | Proposed text posted to list and inserted in 03c, 20070423
30 | 30 | --- | Should source route text be removed entirely and systems prohibited from paying attention to them? |  | Alternative to issue 26
31 | --- | --- | Retain or drop new (03) FTP comparison text?
32 | ---- | --- | Is requirement in section 2.1 that server accept responsibility for messages appropriately stated as MUST? |  | formerly "protocol requires that a server accept"